## Plan
No | Epic | Task | Detail | Assignee | Result | Status | Start date | Due date | Actually started | Actually ended
1 | Find the data | Have to decide what sport and then find the valid data |  | Satoru |  |  | 2022-12-25 | 2022-12-30
2 | Data dictionary | link |  | Satoru |  |  | 2023-01-08 | 2023-01-08
3 | Data analysis |  |  | Satoru |  |  | 2023-01-09 | 2023-01-11
4 | Feature creation | Generated features |  | Satoru
|  | Additional features |  | Satoru
|  | Clustering |  | Satoru
5 | Feature engineering | Outlier cleansing |  | Satoru
|  | Logic checking |  | Satoru
|  | Handle missing value |  | Satoru
6 | Model Experimentation | Train/test split | Train/test split | Satoru
|  | Model Pipeline | Linear methods | Satoru
|  |  | Boosting algorithms | Satoru
Satoru
Satoru
Satoru
|  | Imbalanced data problem solving | Undersampling | Satoru
|  |  | Oversampling | Satoru
|  | Grid Search | Parameter tuning | Satoru
|  | Final | Decide which model to use | Satoru

## Raw Data Dictionary
Column name | Definition | Additional explanation | Numerical/ Categorical | Unique value count | Unique value | Default value | NULL count